## Navigation
Yes
No
Yes
No
No
START PROJECT
Is the process well understood?
SIPOC
Process Map
Are the key variables known?
C&E Matrix
Is the root cause of the problem fully understood?
Would you like to identify further improvement opportunities?
Gemba Walk
Yes
Yes
No
Select a root cause analysis tool
Fishbone Analysis
5Ys
FMEA
Select a tool to prioritise improvement ideas
Pareto Priority Index
Decision Matrix
Eisenhower Matrix
Select a tool to monitor and control improvements
RACI Matrix
Action Plan

## SIPOC
SUPPLIERS | INPUTS | PROCESS STEPS | OUTPUTS | CLIENTS
Overview:
SIPOC stands for Suppliers, Inputs, Process, Outputs and Customers. It is a process mapping and improvement tool that summarises inputs and outputs for each step in a process, as well as suppliers and customers.
Instructions:
Step 1 - Map the Process Steps:
Define 5-10 high level activities to summarise the overall process
"Steps that convert inputs to outputs"
Step 2 - Determine Process Outputs:
Map the outputs from each process step
"Product or service created from the process step"
Step 3 - Identify Customers:
Outline who receives the process outputs
"Recipients of the outputs from the process step"
Step 4 - Determine Process Inputs:
Map the key inputs necessary for completion of the process step
"Resources needed to complete the process step (e.g. materials, services or information)"
Step 5 - Identify Suppliers:
Outline who supplies the inputs required by the process step
"Providers of inputs into a process step (internal or external)"

## C&E Matrix
Rating of Importance to Customer >
LINE | PROCESS STEP | PROCESS INPUT | Project Y1 | Project Y2 | Project Y3 | TOTAL SCORE | Key for Correlation Scoring
1 | [5 empty] | 0 | 0 | No relationship between input and output
2 | [5 empty] | 0 | 1 | Slight relationship between input and output
3 | [5 empty] | 0 | 3 | Average relationship between input and output
4 | [5 empty] | 0 | 9 | Direct relationship between input and output
5 | [5 empty] | 0
6 | [5 empty] | 0
7 | [5 empty] | 0
8 | [5 empty] | 0
9 | [5 empty] | 0
10 | [5 empty] | 0
11 | [5 empty] | 0
12 | [5 empty] | 0
13 | [5 empty] | 0
14 | [5 empty] | 0
15 | [5 empty] | 0
16 | [5 empty] | 0
17 | [5 empty] | 0
18 | [5 empty] | 0
19 | [5 empty] | 0
20 | [5 empty] | 0
Overview:
Cause & Effect (C&E) Matrix is a tool used to prioritise process inputs (or variable) with regards to their influence on the project Ys (or objectives).
Instructions:
Step 1 - Enter Project Ys:
These are the metrics or objectives agreed upon in your project charter (three or more is advisable)
Step 2 - Rate the Importance of the Project Ys:
From the customer's perspective, rank the importance from 1-10 with 10 being most important
Step 3 - List the Process Steps:
These can be taken directly from the SIPOC process map
Step 4 - List the Inputs for Each Process Step:
Each input needs its own row, so the process step will be repeated as many times as there are inputs to that step
Step 5 - Complete Scoring of Correlations:
With a team of SMEs score how strong the relationship is between the process input and each output, using the 0/1/3/9 scale
Step 6 - Prioritising the Inputs:
Sort the 'Total Score' column in descending order using the filter button to prioritise the inputs based on their effect to the ouputs
Step 7 - Select Top Inputs:
Choose the top 3-5 inputs as Key Process Variables (KPVs) to investigate in the FMEA

## 5Ys
PROBLEM STATEMENT
| What caused the specific situation? | Why wasn't the problem detected? | What system(s) failed?
1st Why?
2nd Why?
3rd Why?
4th Why?
5th Why?
Overview:
5Y analysis is a very simple problem solving tool that can be used to determine the root cause of a problem or defect. The idea is to ask the question 'why?' five times, or until you reach the underlying root cause of the problem.
Instructions:
Step 1 - Define Problem Statement:
Describe the problem or defect, including as much detail as possible around the who/what/when/where/how
Step 2 - What Caused the Situation?:
Ask yourself, or the team, why the situation occurred and write the answer as the '1st Why'
Step 3 - Continue Asking Why?:
Looking at the answer for the 1st Why, again, ask why this happened and write the answer as the '2nd Why' - continue this process until the team agrees that the root cause is identified
This may take fewer or more than 5 Whys
Step 4 - Detection and System Failures:
Repeat steps 2 and 3 to answer the questions 'Why wasn't the problem detected?' and 'What system(s) failed?'
Step 5 - Identify Corrective Actions:
Once the root cause is determined, identify and implement corrective actions to either:
a) prevent the situation from re-occurring
b) improve detection of the symptoms that led to the problem
c) minimise risk of systems failing again

## Fishbone Analysis
PEOPLE | MATERIALS | METHOD
PROBLEM STATEMENT
MEASUREMENT | MECHANISM | ENVIRONMENT
Overview:
Fishbone (or Ishikawa, or Cause-and-Effect) Analysis is a problem solving tool that is used to generate a list of potential root causes behind a problem or defect that has occurred. It is typically displayed in the shape of a fishbone and has six sub-sections for investigating the causes behind the effect (i.e. the problem):
People, Materials, Method, Measurement, Machine and Environment.
Instructions:
Step 1 - Define Problem Statement:
Describe the problem or defect, including as much detail as possible around the who/what/when/where/how
Step 2 - People:
List potential causes related to the individuals who are involved in the task
e.g. Human error, untrained operator, etc.
Step 3 - Materials:
List potential causes related to the materials involved in the task
e.g. Expired ingredients, out of spec raw materials, etc.
Step 4 - Method:
List potential causes related to the methods involved in the task
e.g. Order of process steps, wrong settings used, etc.
Step 5 - Measurement:
List potential causes related to the measurements involved in the task
e.g. Equipment calibration, faulty sensors, etc.
Step 6 - Mechanism:
List potential causes related to the measurements involved in the task
e.g. Broken parts, equipment not maintained, etc.
Step 7 - Environment:
List potential causes related to the measurements involved in the task
e.g. Temperature, humidity, background noise, etc.

## FMEA
Process Step | Process Input | Potential Failure Mode | Potential Failure Effects | Severity | Potential Causes | Occurrence | Current Controls | Detection | RPN | Recommended Actions | Responsible | Actions Taken | Severity | Occurrence | Detection | RPN
What is the process step under investigation? | What is the process input under investigation? | In what ways does the input go wrong? | What is the impact on the project Ys? |  | What causes the process input to go wrong? |  | What are the existing controls and procedures that prevent either the cause or the failure mode? |  |  | How can we reduce the RPN by improving either the severity, occurrence or detection? | Who is responsible for completing the action? | What actions have we completed to reduce the RPN?
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
[9 empty] | 0 | [6 empty] | 0
Overview:
Failure Modes and Effects Analysis (FMEA) is a structured approach to identify, prioritise and limit potential failures modes in a process or product. These failures might cause waste, defects, safety concerns or other negative outcomes for the customer.
Instructions:
Step 1 - Enter Process Steps and Inputs:
These are the top 3-5 KPVs identified in your C&E Matrix
Step 2 - Consider the Potential Failure Modes:
A potential failure mode is any way in which the process input could fail to perform its intended function; there are likely multiple failure modes per process input
Step 3 - Determine the Potential Failure Effects:
What would be the consequence of each failure mode, in relation to the project Ys? There are likely multiple effects per failure mode
Step 4 - Assign a Severity Ranking:
Rate the severity of each failure effect on a scale of 1-10 with 10 being the highest, using the dropdown options
Step 5 - Determine Potential Root Causes:
Use knowledge and experience of SMEs, or root cause analysis tools such as 5Ys or Fishbone, to determine causes of each failure mode; there are likely multiple potential causes per failure mode
Step 6 - Assign an Occurrence Ranking:
Rate the likelihood/frequency of each root cause on a scale of 1-10 with 10 being highest, using the dropdown options
Step 7 - Identify Current Process Controls:
For each cause, identify current tests/procedures/mechanisms that are in place to prevent failures from reaching the customer
Step 8 - Assign a Detection Ranking:
Rate the ability of each control to either prevent a failure mode/cause from occurring or detect a failure mode/cause/effect after it has occurred on a scale of 1-10 with 10 being the highest, using the dropdown options
Step 9 - Calculate the Risk Priority Number (RPN):
RPN is a relative risk ranking where a higher RPN translates to a higher potential risk; it is calculated by multiplying the three rankings together
Step 10 - Prioritise the Risks:
Sort the 'RPN' column in descending order using the filter button to prioritise the risks
Step 11 - Develop and Manage Action Plan:
Agree actions to reduce the RPN for high priority risks (by reducing either the severity, occurrence or detection score). Record completed actions and reassign rankings to calculate an improved RPN

## Gemba Walk
WASTE TYPE | OBSERVATIONS | CAUSES | CORRECTIONS
OVER (OR UNDER) PRODUCTION
PEOPLE SKILLS
TRANSPORT
IDLE TIME
MOVEMENT
INVENTORY (ClENTS)
SCRAP
EXTRA PROCESSING
Overview:
A Gemba Walk (or Waste Walk) is a Lean methodology that is used to identify and correct inefficiencies in a workplace. Lean principles categorise eight key sources of waste, which can be remembered using the OPTIMISE acronym:
Over (or Under) Production, People Skills, Transport, Idle Time, Movement, Inventory, Scrap and Extra Processing
Instructions:
Step 1 - Inform the Workers:
The idea of a Gemba Walk is to observe a process in its natural form, so informing workers/operatives in advance is advised so that they're at ease and a true reflection of the process is gained
Step 2 - Visit the Gemba:
Gemba is the Japanese work meaning "the actual place" - therefore a Gemba walk must be conducted in the actual place of work, rather than a meeting room for example
Step 3 - Record Observations:
Observe the process without interfering, whilst recording any source of waste in the relevant category
Step 4 - Determine Causes:
After completion of the Gemba Walk, use tools such as 5Y or Fishbone Analysis to determine the root cause of the waste sources that were observed
Step 5 - Identify Corrective Actions:
Once the root cause is determined, identify and implement corrective actions to eliminate or minimise each source of waste

## Pareto Priority Index
CANDIDATE | ESTIMATED SAVINGS (£k) | SUCCESS PROBABILITY (%) | ESTIMATED COST (£k) | ESTIMATED PROJECT DURATION (Months) | PARETO PRIORITY INDEX
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
Overview:
Pareto Priority Index (PPI) is a method that can be used to prioritise ideas, options or projects based on their benefit, probability of success, cost to implement and resource requirements.
Instructions:
Step 1 - List the Options:
Add each option into a separate row within column A
Step 2 - Estimate Savings:
Estimate the benefit or cost savings of each option, using a consistent format
e.g. If thousands are the relevant format, £500,000 would be "500" and £25,000 would be "25"
Step 3 - Determine Probability of Success:
Using knowledge and experience, assign a % probability of success for each option
e.g. The column is formatted for %, so simply enter "90" for 90%
Step 4 - Estimate Costs:
Estimate the cost required to implement each option, using a consistent format
e.g. If thousands are the relevant format, £10,000 would be "10" and £750 would be "0.75"
Step 5 - Estimate Project Duration:
Estimate the time required to implement each option, using a consistent format
e.g. The suggestion is to use months, however hours/days/weeks/years can be used if relevant
Step 6 - Prioritise Options:
Column F will auto-populate with a PPI score for each option; use the filter to order from largest to smallest and use the insights to select the most appropriate option
PPI increases as savings and probability of success increase
PPI decreases as cost and project duration increase

## Decision Matrix
Rating of Importance >
CANDIDATE | Requirement 1 | Requirement 2 | Requirement 3 | TOTAL SCORE | Key for Satisfaction Scoring
|  |  |  | 0 | 0 | No satisfaction of requirement
|  |  |  | 0 | 1 | Potential to satisfy requirement
|  |  |  | 0 | 3 | Partially satisfies requirement
|  |  |  | 0 | 9 | Completely (or almost) satisfies requirement
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Overview:
A Decision Matrix is a tool that can be used to compare multiple options against one another to find the optimal solution, based on a set of requirements that you determine to be important.
Instructions:
Step 1 - Enter Requirements:
These are the requirements that you value most and can be used to compare the various options (three or more is advisable)
Step 2 - Rate the Importance of the Requirements:
Rank the importance from 1-10 with 10 being most important
Step 3 - List the Options:
Add each option into a separate row within column A
Step 4 - Complete Scoring of Options:
Score how well each option satisfies each requirement, using the dropdown options and 0/1/3/9 scale
Step 6 - Prioritising the Options:
Sort the 'Total Score' column in descending order using the filter button to prioritise the options based on their ability to satisfy requirements

## Eisenhower Matrix
| URGENT | NOT URGENT
IMPORTANT | DO IT | SCHEDULE IT
NOT IMPORTANT | DELEGATE IT | REMOVE IT
Overview:
The Eisenhower Matrix is a tool used to prioritise workload or tasks, based on their importance and urgency. It can be applied to either an individual's to-do list, or to prioritise activities within a larger team project.
Instructions:
Step 1 - Visualise Current Backlog:
Create a list of all tasks in the current backlog, which need to be prioritised
Step 2 - Assign Importance and Urgency:
Based on best knowledge decide whether each task is important or not important and urgent or not urgent, then add it to the relevant quadrant
Step 3 - Take Action:
Tasks which are both important and urgent should be your priority - do it
Tasks which are important but not urgent should be completed by you, but can wait - schedule it
Tasks which are urgent but not important can be completed by someone else - delegate it
Tasks which aren't important or urgent can be removed from your backlog - remove it

## RACI Matrix
PROCESS STEP | JOB ROLE 1 | JOB ROLE 2 | JOB ROLE 3 | JOB ROLE 4 | JOB ROLE 5
Overview:
A RACI Matrix is a project management tool used to outline which individuals or job roles are responsible for each step within an end-to-end process.
R = Responsible
A = Accountable
C = Consulted
I = Informed
Instructions:
Step 1 - List the Process Steps:
These can be taken directly from the SIPOC process map
Step 2 - Identify Job Roles:
List all individuals or job roles that are involved in the process, across row 1
Step 3 - Agree and Assign Responsibilities:
Alongside the project team, assign levels of responsibility (R/A/C/I) for each process step using the dropdown options
Every process step should have at least one 'R'
If a job role is both responsible and accountable, choose the highest level (i.e. R)

## Action Plan
ACTION | SUCCESS CRITERIA | RISKS | RESOURCES REQUIRED | RESPONSIBLE | START DATE | TARGET END DATE | PROGRESS UPDATE | STATUS
Overview:
An Action Plan is a project management tool that lists the action steps required to achieve the project goals and objectives. The action plan outlines what resources are required to achieve those goals, who is responsible for each action and when they should be completed by.
Instructions:
Step 1 - List the Actions:
List all improvement actions identified from previous LSS tools or otherwise
Step 2 - Outline Success Criteria:
Key (ideally measurable) outputs that will determine the success of this action
Step 3 - Identify Risks:
Where possible, foresee potential roadblocks that might hinder progress with the action
Step 4 - Identify Resources Required:
Document what resources will be required to complete each action
e.g. time, support from colleagues, investment, etc.
Step 5 - Agree Responsible Person:
Who is responsible for completing each action?
Step 6 - Agree Completion Timeframe:
Agree a start and target end date for each action
Step 7 - Progress Updates:
At each progress review meeting, write a brief summary to keep record of the most recent update
Either overwrite the previous update, or add a new column for each update
Step 8 - Update Action Status:
Update the status of each task using the dropdown options